## Slide 1: DocuWare (A Document Management System for Gas)
23-Aug-2022
Providing historical scanned mains and service installation records, to office and field crews, in an easy to consume platform-agnostic format, to improve design, operational response time, and safety, using modern digital technology.

## Slide 2: Business Problem: The Case for a New Document Management System
Gas services are not always mapped in the Geographic Information System (GIS) in many NG sub-companies:
Services/Detailed Main as-built records are on scanned cards
These records are in the legacy systems such as:
  Fortis (NY and MA):
    Runs only on Internet Explorer (IE)
    Does not run on IOS devices (since IE is not available for IOS)
    Field staff running IOS (GBE implementation) do not have access to Scanned Records via Fortis
    System runs with great difficulty on Win 10
    The product has been deprecated by the vendor
  DocuFind (RI)
    Is functional limited and cost-prohibitive
Impact To:
  Gas Field Force:
    No access to configuration of service and location of service valve
    Increased risk of incidents and damages due to inability to correctly mark out service locations
    Inability to quickly respond to gas damages to make the location safe
  Gas Engineers:
    Reduced access to service cards for:
      New/relay/abandon main design decisions
      Large gas outages

## Slide 3: Why DocuWare?
A simple easy-to-use / manage Document Management System that:
Is from the same vendor as Fortis:
  Business process very similar to that of Fortis
  Functionally rich from Day 1
  Fully vendor-supported and managed
  Cost-effective
  Clear migration path from Fortis (6M+ document) to DocuWare
Allows:
  Uploading documents and indexing metadata
  Quick retrieval of scanned documents
  Offline access (if/when needed)
Cloud-hosted and accessible from any National Grid “managed” device (running IOS / Windows / Android)
  Runs from any browser
  Ability to use the native IOS/Android App
100% configurable to National Grid’s needs
Is scalable as the types of content and the number of records increases, without perceptible degradation of performance
Is lightweight and fast and can run on mobile software with relatively slower network connections
Has the ability to interfaces with the GBE asset management systems (Esri, Maximo, Salesforce, etc.) using an URL

## Slide 4: Phased Implementation Approach
Phase 1:
RI
  Migrate all data from Fortis
Phase 2:
UNY
  Migrate all data from Fortis
Phase 3:
LI+NYC
  Migrate all data from Fortis
Phase 4:
MA
Phase 0:
ALL
Project Kickoff (Today)
Unified Cross-Jurisdictional Data Model Finalization
Conversion Process Setup
Team Finalization
  Migrate delta (post DocuFind Go-Live to DocuWare cutover date) from DocuFind or Paper
  Migrate all data from Fortis
  ETA for Go-Live by 25-Sep-2020
Completion by 30-Aug-2022
  ETA: 15-Mar-2023
  ETA: 15-Nov-2022
  ETA: 30-Jan-2023
Phase 5:
ALL
  Primary Project Close
  ETA: 31-Mar-2023
FY23
Baseline Conversion from Fortis and Box to DocuWare
FY24
Adding Key Capabilities and Backlog in Fortis/DocuFind
FY24
Integration of DocuWare to GIS, etc.

## Slide 5: Team Composition
Gas Business
  Matt Breslin Jr (Business Strategist)
IT
  Gabriel Regus (Product Owner)
  David Wiig (DocuWare)
  Alex Solovey (Domain Architect)
  Ziad Howlander (Security)
  Jeffrey Norwood (Change Management)
  Bob Terjesen (Damage Prevention: NY)
  James Steadman (E2E Product LeadMichele Rullo )
  Andrea Costa (Business Partnering)
  Abigail Garcia (Service Owner)
  Core Team:
  Support Team:
  John Carlson (Manager, MA Maps & Records)
  Tom Donovan (Manager, NY Maps & Records)
  Chris Spurchise (Field Ops-UNY)
  Susan Roggi (RI Maps & Records)
  Will Nieman (MA Maps & Records)
  Xxx (Change Management)
  Xxx (CMS)
  Xxx (Damage Prevention)
  Michelle Roche (Design and Material Processing)
  DongNi Qui (Construction/Engineering)
  Core Team:
  Shraddha Shinde (Fortis Support)
  Clinton Joshi (DocuFind Support)
  Support Team:
  Ryan Ashton (Security Architect)
  Travis Coleman (Business Partnering)
  Neetu Sahansra (MDM)
  Kaizad Patel (Cloud Engineering)
  Andrew MacDonald (Firewall/Networking)
  Xxx (DNY Maps & Records)
  Molly Grzelka (UNY Clerical Support)
  Surajit Roy-Chowdhury (Product Director)
  Ellen Poyant (E2E Domain Director)
  Pratibha Seetharam (Construction)
  (Work Support)
  Kathleen Finnegan (Work Support)
  Ohsafa Harding (Engineering)
  Michael Amadi (Engineering)
  Mark Huck (Damage Prevention: MA)
  Evan Schierwagen (Field Ops-DNY)
  Artie / Billie C.. / Kevin Mahoney (Field Ops-MA)
  Dennis Ruppert (Corrosion)
  Sean Cunningham (Data)
  Del Sian (Database Architect)
  Kathleen Carr-McCarthy (Data)
  Holly Oyer (Clerical Support)
  Mahaxxx (QES)
Draft

## Slide 6: Appendix

## Slide 7
At a Glance:
Replacing High-Risk Pipeline Assets
1
Assess asset risk profile
2
6
8
5
9
A high-level view of how a main replacement program will be initiated, planned, and executed in the future at National Grid.
10
7
C55 Investment Creation
C55 Optimization and Investment Selection
Initiate project and work orders in Maximo
Schedule & dispatch work
Execute work and record completion details in mobile device
Design work in GWD
Review / approve work order in Maximo
Gather permits, DigSafes, & other pre-requisites
12
13
Supervisor review of work order in Maximo
Review as-built estimate
7
4
11
3
Develop projects based on risk plan
Annual Capital Plan
14
Update GIS with asset details
15
Close financial work order

## Slide 8: At a Glance: Responding to an emergency situation Receive Call and Create the case Initiate Emergency Response Work Order Dispatch the work Assess the situation and make it safe Perform Leak Surveillance Work Update Leak and establish Leak Recheck Perform Leak Recheck Close Leak and analyze leak information Capture leak readings and classify the leak Leak location will be created Create, Schedule and Dispatch Leak Surveillance and Leak Repair Work Perform Leak Repair work
1
2
3
6
9
7
5
4
8
A high-level view of how National Grid team responds to a Grade 2 gas odor call and restores the operations back to normal
11
12
10

## Slide 10: Business Value Roadmap
Iteration 1:
Iteration 3:
System Configuration (Folders and Metadata)
NG Sample Data Import
Demo
Setup of Sandbox Environment
Iteration 4:
Demo
UI Development: Indexing
UI Development: File Upload
Demo
Iteration 2:
Iteration 5:
Iteration 6:
End-to-End Testing (Initial)
Demo
Iteration 7:
UAT
Iteration 8:
Demo
Iteration 9:
Demo
Iteration 10:
Iteration 16:
Planning for Rollout
Iteration 17:
Service Transition Document Approval
Training Content Development
UI Development: Search and Display
Demo
UI Development: Editing
Demo
Demo
Defect Prioritization
Defect Fixing 1
Defect Fixing 2
UAT
Sign-Off
Demo
Service Transition Document Build
Iteration 18:
RI Delta Sync
RI Rollout
Iteration 20:
LI Delta Sync
LI Rollout
Iteration 21:
NYC Delta Sync
NYC Rollout
Iteration 22:
MA Delta Sync
MA Rollout
Phase 2 (In 1-2 Years):
Migration to Enterprise DMS
Iteration 11:
RI Full Data Conversion
Iteration 13:
LI Full Data Conversion
Iteration 14:
NYC Full Data Conversion
RI Full Data Import
LI Full Data Import
NYC Full Data Import
MA Full Data Conversion
MA Full Data Import
Iteration 15:
Iteration 12:
UNY Full Data Conversion
UNY Full Data Import
Iteration 19:
UNY Delta Sync
UNY Rollout
Iteration 23:
Phase 1 PGLS
Phase 1 Closeout